Minutes of NPCC meeting 6.30pm, Tuesday, 25th November 2014

Held in Watlington Parish Office

Present:

Nick Hancock - Chairman

Andy Hocking

Rhian Woods

Neil Boddington – from 104/14

Officer: 	Rachel Gill

In attendance: 	Ian Hill

99/14 Apologies for Absence

Neil Mitchenall

100/14 To agree the Minutes of the 3rd November 2014 as a correct record of the meeting.

The following changes were agreed.

Minutes 91/14 refers – Present: change to – Neil Mitchenall from agenda item 91/14, Rhian woods from agenda item 91/14, Neil Boddington present from agenda item 91/14

94/14 delete sentence “He has suggested…”98/10 Next Meeting of the NPCC, change to Minute number 98/14

Resolved: That these minutes with the above changes be agreed and signed by the Chairman.

101/14 Declarations of interest

There were no declarations of interest declared.

102/14 Matters arising from the minutes of 3rd November

Minute 90/14 refers – A letter has been sent to Gill Bindoff

Minute 96/14 refers – Consultation 2 has been extended to run from 1 December to 31 January.

103/14 Sustainability Appraisal

NH discussed the process and terminology, which to date has been somewhat confused. A Scoping Report needs to be written before the draft Plan is written and should be included in the Consultation 2 by 16th January. The Scoping Report defines the project plan for creating the NP, the methodology, identifies key features of the plan area and the issues associated with key features which the NP should attempt to

Page 26

address. The Draft Plan is then created and a Sustainability Appraisal carried out by comparing the NP actions with the issues identified in the Scoping Report.

Ian hill has offered to produce the Scoping Report with input from Robert Barber, (aided by the Environment Sustainability group) and NH.

ACTION IH: The first action is to summarise the SWOT list produced by the ES group.

The author(s) of the Sustainability Appraisal should ideally include representatives from outside the NPCC to ensure impartiality.

ACTION NH: Ask David Tindale if the NPSG can take on this responsibility

104/14 Consultation 2 preparation

The document managed by AH will be finished by 28 November.

Key inputs still require are:

- Summary of the TPP report

- Completion of Appendices as per the list of items identified in the document

- Completion of the sites assessment

A standard template should be used for all documents, IH has produced this previously

All documentation should use the new NP logo to provide a separate identity to Parish Council documents

ACTION AH: Manage the document production

ACTION NH and IH: Provide comments by 26 Nov. NH to sign-off by 28 Nov

Web site to be updated to draw attention to Consultation 2, the associated documents and the response form

ACTION RG: Update website

The Consultation 2 document must be sent to all Statutory Consultees, NH has a list from SODC and will send to RG for distribution.

Events supporting the consultation were discussed. It was agreed we should try to run three: 2 Town Hall Saturday morning drop-in sessions and a presentation/exhibition at the Memorial Club. The town Hall sessions should be run one before and one after Christmas, the Memorial Club session after Christmas. It was noted that with all the other activity and the Christmas/New Year interlude this may be a too ambitious schedule of events, especially when combined with other publicity required surrounding the consultation.

ACTION NH: review with Peter Richardson and produce a list of events.

ACTION NH: to produce a list of Consultation 2 and workshop-related collateral required over the next 2 months.

Page 27

105/14 Possible funding sources

Both SODC and OCC may have access to significant funding to help progress actions identified in the NP. The Economic Vitality Fund, The Rural Infrastructure Fund and the European Structural and Investment Fund have all been mentioned.

Anna Badcock may have access to some EVF monies.

ACTION NH NB: to meet SODC and OCC before Christmas if possible

ACTION NM: to meet Anna B

106/14 Traffic Think Tank

Following the TPP report and the presentation to the community RW has suggested establishment of a think tank to consider traffic-related options. This group would include, aside from key NPCC members (RW, NM?) and local experts and those volunteers with specialist skills. The group should probably only number around 6 and not be established as a formal meeting but perhaps meet once or twice with the specific aim of reviewing and identifying options to reduce the impact of traffic at both current volumes and the predicted growth during the period of the NP (to 2031).

This group should aim to conclude any work before February to provide input to the Draft Plan

ACTION RW: discuss with NM and determine membership and meeting dates

Regarding the other apparent 17 traffic-issue volunteers it was agreed that 17 was too large a number to manage. However their input was welcomed and some maybe asked to contribute to the Traffic Think Tank. It will be pointed out to the volunteers that they are free to and encouraged to organise a meeting on traffic as they think fit and feedback to NPCC and/or the Traffic Think Tank.

ACTION NH, RG: draft letter from the Parish Office to the 17 thanking them for their offer.

107/14 Date of next meeting

ACTION NH: to determine

There being no other business the meeting closed at 8.00pm

Page 28